## Data
Tasks | Start date | End date | Duration
Requirement Gathering | 2025-02-01 | 2025-02-05 | 4
Literature Survey | 2025-02-06 | 2025-02-11 | 5
Zeroth Review | 2025-02-11 | 2025-02-12 | 1
Develop Preprocessing Pipeline | 2025-02-17 | 2025-02-24 | 7
Integrate OCR and Translation Models | 2025-02-26 | 2025-03-04 | 6
First Review | 2025-03-04 | 2025-03-05 | 1
Implement Backend with Processing Pipeline | 2025-03-10 | 2025-03-12 | 2
Build Logic for Converting Results to TXT, PDF, DOCX | 2025-03-13 | 2025-03-16 | 3
Develop User Interface | 2025-03-17 | 2025-03-21 | 4
Integrate Frontend and Backend | 2025-03-24 | 2025-03-28 | 4
Second Review | 2025-04-01 | 2025-04-02 | 1
Evaluate System Performance, Accuracy, and Usability | 2025-04-07 | 2025-04-11 | 4
Finalize Prototype | 2025-04-12 | 2025-04-16 | 4
Prepare Project Documentation | 2025-04-18 | 2025-04-25 | 7
Final Review | 2025-04-29 | 2025-04-30 | 1